## Repo Clone Timeline
Task ID | Phase | Exact Task | Start Date | End Date | Duration (Days) | Owner | Priority | Status
RC1 | Repository Setup | Create KV Greens GitHub repository | 2026-02-23 | 2026-02-23 | 1 | Developer | High | Pending
RC2 | Repository Setup | Clone Vasave/Bansi base repository | 2026-02-24 | 2026-02-24 | 1 | Developer | High | Pending
RC3 | Repository Setup | Remove old git history & reinitialize | 2026-02-25 | 2026-02-25 | 1 | Developer | High | Pending
RC4 | Configuration | Update project name & metadata | 2026-02-26 | 2026-02-27 | 2 | Developer | High | Pending
RC5 | Configuration | Update environment variables | 2026-02-28 | 2026-03-01 | 2 | Developer | High | Pending
RC6 | Branding | Replace logo and brand assets | 2026-03-02 | 2026-03-03 | 2 | Designer | High | Pending
RC7 | Branding | Update color theme (CSS variables) | 2026-03-04 | 2026-03-05 | 2 | Developer | Medium | Pending
RC8 | Content Update | Edit homepage content | 2026-03-06 | 2026-03-08 | 3 | Content Team | High | Pending
RC9 | Content Update | Replace all images with KV Greens media | 2026-03-09 | 2026-03-10 | 2 | Content Team | High | Pending
RC10 | Content Update | Update About & Operations pages | 2026-03-11 | 2026-03-13 | 3 | Content Team | High | Pending
RC11 | Compliance | Update Privacy Policy & Terms | 2026-03-14 | 2026-03-15 | 2 | Legal | High | Pending
RC12 | SEO | Update meta titles & descriptions | 2026-03-16 | 2026-03-17 | 2 | Marketing | Medium | Pending
RC13 | Testing | Responsive & mobile testing | 2026-03-18 | 2026-03-19 | 2 | QA | High | Pending
RC14 | Testing | Cross-browser testing | 2026-03-20 | 2026-03-21 | 2 | QA | High | Pending
RC15 | Optimization | Performance & speed optimization | 2026-03-22 | 2026-03-23 | 2 | Developer | Medium | Pending
RC16 | Deployment | Setup hosting & SSL | 2026-03-24 | 2026-03-25 | 2 | IT | High | Pending
RC17 | Deployment | Deploy to production server | 2026-03-26 | 2026-03-26 | 1 | Developer | High | Pending
RC18 | Post Launch | Setup automated backups & monitoring | 2026-03-27 | 2026-03-28 | 2 | IT | High | Pending