## Repo Clone Website Plan
Task ID | Phase | Exact Task | Description | Owner | Start Date | End Date | Status
RC1 | Repository Setup | Create New Git Repository | Create KV Greens repository in GitHub | Developer |  |  | Pending
RC2 | Repository Setup | Clone Base Repository | Clone Vasave/Bansi website repository locally | Developer |  |  | Pending
RC3 | Repository Setup | Remove Old Git History | Detach old repo and initialize new git history | Developer |  |  | Pending
RC4 | Configuration | Update Project Name | Change project name to KV Greens | Developer |  |  | Pending
RC5 | Configuration | Update Environment Variables | Update API URLs, base paths, metadata | Developer |  |  | Pending
RC6 | Branding | Replace Logo | Upload KV Greens logo | Designer |  |  | Pending
RC7 | Branding | Update Color Theme | Change CSS variables to green theme | Developer |  |  | Pending
RC8 | Content Update | Edit Homepage Content | Replace text with KV Greens content | Content Team |  |  | Pending
RC9 | Content Update | Replace Images | Upload farming & forestry images | Content Team |  |  | Pending
RC10 | Content Update | Update About Page | Add KV Greens company info | Content Team |  |  | Pending
RC11 | Content Update | Update Services/Operations Page | Add farming & forestry operations | Content Team |  |  | Pending
RC12 | Compliance | Update Privacy Policy | Insert KV Greens legal details | Legal |  |  | Pending
RC13 | Compliance | Update Terms & Conditions | Company specific legal content | Legal |  |  | Pending
RC14 | Technical | Test Responsiveness | Check mobile and tablet layout | QA |  |  | Pending
RC15 | Technical | SEO Metadata Update | Update meta titles & descriptions | Marketing |  |  | Pending
RC16 | Testing | Cross Browser Testing | Chrome, Edge, Safari testing | QA |  |  | Pending
RC17 | Deployment | Setup Hosting | Configure hosting server | IT |  |  | Pending
RC18 | Deployment | Deploy Website | Push code to production | Developer |  |  | Pending
RC19 | Post Launch | Setup Backup System | Enable automated backups | IT |  |  | Pending